## Tier 1
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2018
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2017-10-31 | 2017-11-22 | 2017-11-29 | 2017-12-05 | 2017-11-29 | 2017-11-29 | 2017-12-07 |  | 2017-12-14 | 2017-12-26 | 2018-01-24 | 2018-01-09 | 2018-02-28 | 56 | 70
2017-12-01 | 2017-12-25 | 2018-01-02 | 2018-01-08 | 2018-01-02 | 2018-01-02 | 2018-01-10 |  | 2018-01-19 | 2018-01-23 | 2018-02-28 | 2018-02-13 | 2018-03-28 | 53 | 74
2017-12-28 | 2018-01-24 | 2018-01-31 | 2018-02-06 | 2018-01-31 | 2018-01-31 | 2018-02-08 |  | 2018-02-15 | 2018-02-27 | 2018-03-28 | 2018-03-13 | 2018-04-25 | 61 | 75
2018-01-30 | 2018-02-22 | 2018-03-01 | 2018-03-07 | 2018-03-01 | 2018-03-01 | 2018-03-09 |  | 2018-03-16 | 2018-03-27 | 2018-04-25 | 2018-04-10 | 2018-05-23 | 56 | 70
2018-02-28 | 2018-03-22 | 2018-03-29 | 2018-04-04 | 2018-03-29 | 2018-03-29 | 2018-04-06 |  | 2018-04-13 | 2018-04-24 | 2018-05-23 | 2018-05-08 | 2018-06-20 | 55 | 69
2018-04-03 | 2018-04-25 | 2018-05-02 | 2018-05-08 | 2018-05-02 | 2018-05-02 | 2018-05-10 |  | 2018-05-17 | 2018-05-22 | 2018-06-20 | 2018-06-12 | 2018-07-25 | 49 | 70
2018-04-30 | 2018-05-22 | 2018-05-30 | 2018-06-05 | 2018-05-30 | 2018-05-30 | 2018-06-07 |  | 2018-06-14 | 2018-06-26 | 2018-07-25 | 2018-07-10 | 2018-08-22 | 57 | 71
2018-06-05 | 2018-06-27 | 2018-07-05 | 2018-07-11 | 2018-07-05 | 2018-07-05 | 2018-07-13 |  | 2018-07-20 | 2018-07-24 | 2018-08-22 | 2018-08-14 | 2018-09-26 | 49 | 70
2018-07-02 | 2018-07-25 | 2018-08-01 | 2018-08-07 | 2018-08-01 | 2018-08-01 | 2018-08-09 |  | 2018-08-16 | 2018-08-28 | 2018-09-26 | 2018-09-11 | 2018-10-24 | 57 | 71
2018-07-30 | 2018-08-21 | 2018-08-28 | 2018-09-04 | 2018-08-28 | 2018-08-28 | 2018-09-06 |  | 2018-09-13 | 2018-09-25 | 2018-10-24 | 2018-10-09 | 2018-11-14 | 57 | 71
2018-08-27 | 2018-09-19 | 2018-09-26 | 2018-10-02 | 2018-09-26 | 2018-09-26 | 2018-10-04 |  | 2018-10-12 | 2018-10-23 | 2018-11-21 | 2018-11-06 | 2018-12-19 | 57 | 71
2018-09-20 | 2018-10-15 | 2018-10-22 | 2018-10-26 | 2018-10-22 | 2018-10-22 | 2018-10-30 |  | 2018-11-06 | 2018-11-20 | 2018-12-19 | 2018-12-04 | 2019-01-23 | 61 | 75
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2019
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2018-10-24 | 2018-11-16 | 2018-11-27 | 2018-12-03 | 2018-11-27 | 2018-11-27 | 2018-12-05 |  | 2018-12-12 | 2019-01-22 | 2019-02-13 | 2019-01-08 | 2019-02-27 | 90 | 76
2018-11-29 | 2018-12-21 | 2018-12-31 | 2019-01-07 | 2018-12-31 | 2018-12-31 | 2019-01-09 |  | 2019-01-16 | 2019-01-22 | 2019-02-27 | 2019-02-12 | 2019-03-20 | 54 | 75
2018-12-28 | 2019-01-24 | 2019-01-31 | 2019-02-06 | 2019-01-31 | 2019-01-31 | 2019-02-08 |  | 2019-02-15 | 2019-02-26 | 2019-03-20 | 2019-03-12 | 2019-04-24 | 60 | 74
2019-01-30 | 2019-02-21 | 2019-02-28 | 2019-03-06 | 2019-02-28 | 2019-02-28 | 2019-03-08 |  | 2019-03-15 | 2019-03-26 | 2019-04-24 | 2019-04-09 | 2019-05-22 | 55 | 69
2019-02-27 | 2019-03-21 | 2019-03-28 | 2019-04-03 | 2019-03-28 | 2019-03-28 | 2019-04-05 |  | 2019-04-12 | 2019-04-23 | 2019-05-22 | 2019-05-07 | 2019-06-26 | 55 | 69
2019-04-02 | 2019-04-24 | 2019-05-01 | 2019-05-07 | 2019-05-01 | 2019-05-01 | 2019-05-09 |  | 2019-05-16 | 2019-05-21 | 2019-06-26 | 2019-06-11 | 2019-07-24 | 49 | 70
2019-04-29 | 2019-05-21 | 2019-05-29 | 2019-06-04 | 2019-05-29 | 2019-05-29 | 2019-06-06 |  | 2019-06-13 | 2019-06-25 | 2019-07-24 | 2019-07-09 | 2019-08-21 | 57 | 71
2019-06-04 | 2019-06-26 | 2019-07-03 | 2019-07-10 | 2019-07-03 | 2019-07-03 | 2019-07-12 |  | 2019-07-19 | 2019-07-23 | 2019-08-21 | 2019-08-13 | 2019-09-25 | 49 | 70
2019-07-01 | 2019-07-24 | 2019-07-31 | 2019-08-06 | 2019-07-31 | 2019-07-31 | 2019-08-08 |  | 2019-08-15 | 2019-08-27 | 2019-09-25 | 2019-09-10 | 2019-10-23 | 57 | 71
2019-07-30 | 2019-08-21 | 2019-08-28 | 2019-09-04 | 2019-08-28 | 2019-08-28 | 2019-09-06 |  | 2019-09-13 | 2019-09-24 | 2019-10-23 | 2019-10-08 | 2019-11-13 | 56 | 70
2019-08-26 | 2019-09-18 | 2019-09-25 | 2019-10-01 | 2019-09-25 | 2019-09-25 | 2019-10-03 |  | 2019-10-10 | 2019-10-22 | 2019-11-13 | 2019-11-05 | 2019-12-18 | 57 | 71
2019-09-26 | 2019-10-21 | 2019-10-28 | 2019-11-01 | 2019-10-28 | 2019-10-28 | 2019-11-05 |  | 2019-11-13 | 2019-11-17 | 2019-12-18 | 2019-12-10 | 2020-01-22 | 52 | 75
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2020
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2019-10-23 | 2019-11-15 | 2019-11-22 | 2019-12-02 | 2019-11-22 | 2019-11-22 | 2019-12-04 |  | 2019-12-11 | 2019-12-17 | 2020-01-22 | 2020-01-07 | 2020-02-26 | 55 | 76
2019-11-26 | 2019-12-20 | 2019-12-30 | 2020-01-06 | 2019-12-30 | 2019-12-30 | 2020-01-08 |  | 2020-01-15 | 2020-01-28 | 2020-02-26 | 2020-02-11 | 2020-03-25 | 63 | 77
2019-12-26 | 2020-01-22 | 2020-01-29 | 2020-02-04 | 2020-01-29 | 2020-01-29 | 2020-02-06 |  | 2020-02-13 | 2020-02-25 | 2020-03-25 | 2020-03-10 | 2020-04-22 | 61 | 75
2020-01-28 | 2020-02-20 | 2020-02-27 | 2020-03-04 | 2020-02-27 | 2020-02-27 | 2020-03-06 |  | 2020-03-13 | 2020-03-24 | 2020-04-22 | 2020-04-07 | 2020-05-27 | 56 | 70
2020-02-26 | 2020-03-19 | 2020-03-26 | 2020-04-01 | 2020-03-26 | 2020-03-26 | 2020-04-03 |  | 2020-04-10 | 2020-04-21 | 2020-05-27 | 2020-05-05 | 2020-06-24 | 55 | 69
2020-03-31 | 2020-04-22 | 2020-04-29 | 2020-05-05 | 2020-04-29 | 2020-04-29 | 2020-05-07 |  | 2020-05-14 | 2020-05-19 | 2020-06-24 | 2020-06-09 | 2020-07-22 | 49 | 70
2020-04-28 | 2020-05-20 | 2020-05-28 | 2020-06-03 | 2020-05-28 | 2020-05-28 | 2020-06-05 |  | 2020-06-12 | 2020-06-23 | 2020-07-22 | 2020-07-07 | 2020-08-26 | 56 | 70
2020-06-03 | 2020-06-25 | 2020-07-02 | 2020-07-08 | 2020-07-02 | 2020-07-02 | 2020-07-10 |  | 2020-07-17 | 2020-07-21 | 2020-08-26 | 2020-08-11 | 2020-09-23 | 48 | 69
2020-06-30 | 2020-07-22 | 2020-07-29 | 2020-08-04 | 2020-07-29 | 2020-07-29 | 2020-08-06 |  | 2020-08-13 | 2020-08-25 | 2020-09-23 | 2020-09-08 | 2020-10-21 | 56 | 70
2020-07-28 | 2020-08-19 | 2020-08-26 | 2020-09-01 | 2020-08-26 | 2020-08-26 | 2020-09-03 |  | 2020-09-11 | 2020-09-22 | 2020-10-21 | 2020-10-06 | 2020-11-18 | 56 | 70
2020-08-25 | 2020-09-17 | 2020-09-24 | 2020-09-30 | 2020-09-24 | 2020-09-24 | 2020-10-02 |  | 2020-10-09 | 2020-10-20 | 2020-11-18 | 2020-11-04 | 2020-12-16 | 56 | 71
2020-09-24 | 2020-10-19 | 2020-10-26 | 2020-10-30 | 2020-10-26 | 2020-10-26 | 2020-11-03 |  | 2020-11-10 | 2020-11-17 | 2020-12-16 | 2020-12-08 | 2021-01-20 | 54 | 75
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2021
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2020-10-28 | 2020-11-20 | 2020-12-01 | 2020-12-07 | 2020-12-01 | 2020-12-01 | 2020-12-09 |  | 2020-12-16 | 2020-12-15 | 2021-01-20 | 2021-01-12 | 2021-02-24 | 48 | 76
2020-11-24 | 2020-12-18 | 2020-12-28 | 2021-01-04 | 2020-12-28 | 2020-12-28 | 2021-01-06 |  | 2021-01-13 | 2021-01-26 | 2021-02-24 | 2021-02-09 | 2021-03-24 | 63 | 77
2020-12-23 | 2021-01-20 | 2021-01-27 | 2021-02-02 | 2021-01-27 | 2021-01-27 | 2021-02-04 |  | 2021-02-11 | 2021-02-23 | 2021-03-24 | 2021-03-09 | 2021-04-28 | 62 | 76
2021-02-02 | 2021-02-25 | 2021-03-04 | 2021-03-10 | 2021-03-04 | 2021-03-04 | 2021-03-12 |  | 2021-03-19 | 2021-03-23 | 2021-04-28 | 2021-04-13 | 2021-05-26 | 49 | 70
2021-03-03 | 2021-03-25 | 2021-04-01 | 2021-04-07 | 2021-04-01 | 2021-04-01 | 2021-04-09 |  | 2021-04-16 | 2021-04-27 | 2021-05-26 | 2021-05-11 | 2021-06-23 | 55 | 69
2021-03-30 | 2021-04-21 | 2021-04-28 | 2021-05-04 | 2021-04-28 | 2021-04-28 | 2021-05-06 |  | 2021-05-13 | 2021-05-25 | 2021-06-23 | 2021-06-08 | 2021-07-28 | 56 | 70
2021-05-03 | 2021-05-25 | 2021-06-02 | 2021-06-08 | 2021-06-02 | 2021-06-02 | 2021-06-10 |  | 2021-06-17 | 2021-06-22 | 2021-07-28 | 2021-07-13 | 2021-08-25 | 50 | 71
2021-06-01 | 2021-06-23 | 2021-06-30 | 2021-07-07 | 2021-06-30 | 2021-06-30 | 2021-07-09 |  | 2021-07-16 | 2021-07-27 | 2021-08-25 | 2021-08-10 | 2021-09-22 | 56 | 70
2021-07-06 | 2021-07-28 | 2021-08-04 | 2021-08-10 | 2021-08-04 | 2021-08-04 | 2021-08-12 |  | 2021-08-19 | 2021-08-24 | 2021-09-22 | 2021-09-14 | 2021-10-27 | 49 | 70
2021-08-02 | 2021-08-24 | 2021-08-31 | 2021-09-07 | 2021-08-31 | 2021-08-31 | 2021-09-09 |  | 2021-09-16 | 2021-09-28 | 2021-10-27 | 2021-10-12 | 2021-11-17 | 57 | 71
2021-08-30 | 2021-09-22 | 2021-09-29 | 2021-10-05 | 2021-09-29 | 2021-09-29 | 2021-10-07 |  | 2021-10-15 | 2021-10-26 | 2021-11-17 | 2021-11-09 | 2021-12-15 | 57 | 71
2021-09-23 | 2021-10-18 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-25 | 2021-11-02 |  | 2021-11-09 | 2021-11-23 | 2021-12-15 | 2021-12-07 | 2022-01-19 | 61 | 75
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2022
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2021-10-29 | 2021-11-23 | 2021-12-02 | 2021-12-08 | 2021-12-02 | 2021-12-02 | 2021-12-10 |  | 2021-12-17 | 2021-12-21 | 2022-01-19 | 2022-01-11 | 2022-02-23 | 53 | 74
2021-11-29 | 2021-12-21 | 2021-12-28 | 2022-01-03 | 2021-12-28 | 2021-12-28 | 2022-01-05 |  | 2022-01-12 | 2022-01-25 | 2022-02-23 | 2022-02-08 | 2022-03-23 | 57 | 71
2021-12-24 | 2022-01-19 | 2022-01-26 | 2022-02-01 | 2022-01-26 | 2022-01-26 | 2022-02-03 |  | 2022-02-10 | 2022-02-22 | 2022-03-23 | 2022-03-08 | 2022-04-27 | 60 | 74
2022-02-01 | 2022-02-24 | 2022-03-03 | 2022-03-09 | 2022-03-03 | 2022-03-03 | 2022-03-11 |  | 2022-03-18 | 2022-03-22 | 2022-04-27 | 2022-04-12 | 2022-05-25 | 49 | 70
2022-03-02 | 2022-03-24 | 2022-03-31 | 2022-04-06 | 2022-03-31 | 2022-03-31 | 2022-04-08 |  | 2022-04-15 | 2022-04-26 | 2022-05-25 | 2022-05-10 | 2022-06-22 | 55 | 69
2022-03-29 | 2022-04-20 | 2022-04-27 | 2022-05-03 | 2022-04-27 | 2022-04-27 | 2022-05-05 |  | 2022-05-12 | 2022-05-24 | 2022-06-22 | 2022-06-07 | 2022-07-27 | 56 | 70
2022-05-02 | 2022-05-24 | 2022-06-01 | 2022-06-07 | 2022-06-01 | 2022-06-01 | 2022-06-09 |  | 2022-06-16 | 2022-06-21 | 2022-07-27 | 2022-07-12 | 2022-08-24 | 50 | 71
2022-05-31 | 2022-06-22 | 2022-06-29 | 2022-07-06 | 2022-06-29 | 2022-06-29 | 2022-07-08 |  | 2022-07-15 | 2022-07-26 | 2022-08-24 | 2022-08-09 | 2022-09-28 | 56 | 70
2022-07-05 | 2022-07-27 | 2022-08-03 | 2022-08-09 | 2022-08-03 | 2022-08-03 | 2022-08-11 |  | 2022-08-18 | 2022-08-23 | 2022-09-28 | 2022-09-13 | 2022-10-26 | 49 | 70
2022-08-01 | 2022-08-23 | 2022-08-30 | 2022-09-06 | 2022-08-30 | 2022-08-30 | 2022-09-08 |  | 2022-09-15 | 2022-09-27 | 2022-10-26 | 2022-10-11 | 2022-11-16 | 57 | 71
2022-08-30 | 2022-09-22 | 2022-09-29 | 2022-10-05 | 2022-09-29 | 2022-09-29 | 2022-10-07 |  | 2022-10-17 | 2022-10-25 | 2022-11-16 | 2022-11-09 | 2022-12-14 | 56 | 71
2022-09-22 | 2022-10-17 | 2022-10-24 | 2022-10-28 | 2022-10-24 | 2022-10-24 | 2022-11-01 |  | 2022-11-08 | 2022-11-22 | 2022-12-14 | 2022-12-06 | 2023-01-18 | 61 | 75
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2023
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2022-10-26 | 2022-11-18 | 2022-11-29 | 2022-12-05 | 2022-11-29 | 2022-11-29 | 2022-12-07 |  | 2022-12-14 | 2022-12-20 | 2023-01-18 | 2023-01-10 | 2023-02-22 | 55 | 76
2022-12-01 | 2022-12-23 | 2023-01-03 | 2023-01-09 | 2023-01-03 | 2023-01-03 | 2023-01-11 |  | 2023-01-20 | 2023-01-24 | 2023-02-22 | 2023-02-14 | 2023-03-22 | 54 | 75
2022-12-29 | 2023-01-25 | 2023-02-01 | 2023-02-07 | 2023-02-01 | 2023-02-01 | 2023-02-09 |  | 2023-02-16 | 2023-02-28 | 2023-03-22 | 2023-03-14 | 2023-04-26 | 61 | 75
2023-01-31 | 2023-02-23 | 2023-03-02 | 2023-03-08 | 2023-03-02 | 2023-03-02 | 2023-03-10 |  | 2023-03-17 | 2023-03-28 | 2023-04-26 | 2023-04-11 | 2023-05-24 | 56 | 70
2023-03-01 | 2023-03-23 | 2023-03-30 | 2023-04-05 | 2023-03-30 | 2023-03-30 | 2023-04-07 |  | 2023-04-14 | 2023-04-25 | 2023-05-24 | 2023-05-09 | 2023-06-21 | 55 | 69
2023-03-28 | 2023-04-19 | 2023-04-26 | 2023-05-02 | 2023-04-26 | 2023-04-26 | 2023-05-04 |  | 2023-05-11 | 2023-05-23 | 2023-06-21 | 2023-06-06 | 2023-07-26 | 56 | 70
2023-05-01 | 2023-05-23 | 2023-05-31 | 2023-06-06 | 2023-05-31 | 2023-05-31 | 2023-06-08 |  | 2023-06-15 | 2023-06-20 | 2023-07-26 | 2023-07-11 | 2023-08-23 | 50 | 71
2023-05-30 | 2023-06-21 | 2023-06-28 | 2023-07-05 | 2023-06-28 | 2023-06-28 | 2023-07-07 |  | 2023-07-14 | 2023-07-25 | 2023-08-23 | 2023-08-08 | 2023-09-27 | 56 | 70
2023-07-03 | 2023-07-26 | 2023-08-02 | 2023-08-08 | 2023-08-02 | 2023-08-02 | 2023-08-10 |  | 2023-08-17 | 2023-08-22 | 2023-09-27 | 2023-09-12 | 2023-10-25 | 50 | 71
2023-07-31 | 2023-08-22 | 2023-08-29 | 2023-09-05 | 2023-08-29 | 2023-08-29 | 2023-09-07 |  | 2023-09-14 | 2023-09-26 | 2023-10-25 | 2023-10-10 | 2023-11-15 | 57 | 71
2023-08-30 | 2023-09-22 | 2023-09-29 | 2023-10-05 | 2023-09-29 | 2023-09-29 | 2023-10-10 |  | 2023-10-17 | 2023-10-24 | 2023-11-15 | 2023-11-09 | 2023-12-13 | 55 | 71
2023-09-21 | 2023-10-16 | 2023-10-23 | 2023-10-27 | 2023-10-23 | 2023-10-23 | 2023-10-31 |  | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2023-12-05 | 2024-01-17 | 61 | 75
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2024
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2023-10-25 | 2023-11-17 | 2023-11-28 | 2023-12-04 | 2023-11-28 | 2023-11-28 | 2023-12-06 |  | 2023-12-13 | 2023-12-19 | 2024-01-17 | 2024-01-09 | 2024-02-28 | 55 | 76
2023-12-01 | 2023-12-26 | 2024-01-03 | 2024-01-09 | 2024-01-03 | 2024-01-03 | 2024-01-11 |  | 2024-01-19 | 2024-01-23 | 2024-02-28 | 2024-02-13 | 2024-03-27 | 53 | 74
2023-12-29 | 2024-01-24 | 2024-01-31 | 2024-02-06 | 2024-01-31 | 2024-01-31 | 2024-02-08 |  | 2024-02-15 | 2024-02-27 | 2024-03-27 | 2024-03-12 | 2024-04-24 | 60 | 74
2024-01-30 | 2024-02-22 | 2024-02-29 | 2024-03-06 | 2024-02-29 | 2024-02-29 | 2024-03-08 |  | 2024-03-15 | 2024-03-26 | 2024-04-24 | 2024-04-09 | 2024-05-22 | 56 | 70
2024-03-06 | 2024-03-28 | 2024-04-04 | 2024-04-10 | 2024-04-04 | 2024-04-04 | 2024-04-12 |  | 2024-04-19 | 2024-04-23 | 2024-05-22 | 2024-05-14 | 2024-06-26 | 48 | 69
2024-04-02 | 2024-04-24 | 2024-05-01 | 2024-05-07 | 2024-05-01 | 2024-05-01 | 2024-05-09 |  | 2024-05-16 | 2024-05-28 | 2024-06-26 | 2024-06-11 | 2024-07-24 | 56 | 70
2024-04-26 | 2024-05-20 | 2024-05-28 | 2024-06-03 | 2024-05-28 | 2024-05-28 | 2024-06-05 |  | 2024-06-12 | 2024-06-25 | 2024-07-24 | 2024-07-09 | 2024-08-28 | 60 | 74
2024-06-03 | 2024-06-26 | 2024-07-03 | 2024-07-10 | 2024-07-03 | 2024-07-03 | 2024-07-12 |  | 2024-07-19 | 2024-07-23 | 2024-08-28 | 2024-08-13 | 2024-09-25 | 50 | 71
2024-07-01 | 2024-07-24 | 2024-07-31 | 2024-08-06 | 2024-07-31 | 2024-07-31 | 2024-08-08 |  | 2024-08-15 | 2024-08-27 | 2024-09-25 | 2024-09-10 | 2024-10-23 | 57 | 71
2024-07-30 | 2024-08-21 | 2024-08-28 | 2024-09-04 | 2024-08-28 | 2024-08-28 | 2024-09-06 |  | 2024-09-13 | 2024-09-24 | 2024-10-23 | 2024-10-08 | 2024-11-27 | 56 | 70
2024-08-29 | 2024-09-23 | 2024-09-30 | 2024-10-04 | 2024-09-30 | 2024-09-30 | 2024-10-08 |  | 2024-10-16 | 2024-10-22 | 2024-11-27 | 2024-11-12 | 2024-12-18 | 54 | 75
2024-09-24 | 2024-10-17 | 2024-10-24 | 2024-10-30 | 2024-10-24 | 2024-10-24 | 2024-11-01 |  | 2024-11-12 | 2024-11-26 | 2024-12-18 | 2024-12-09 | 2025-01-22 | 63 | 76
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2025
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2024-10-29 | 2024-11-22 | 2024-12-03 | 2024-12-09 | 2024-12-03 | 2024-12-03 | 2024-12-11 |  | 2024-12-18 | 2024-12-17 | 2024-01-24 | 2025-01-14 | 2025-02-26 | 49 | 77
2024-11-27 | 2024-12-23 | 2024-12-31 | 2025-01-07 | 2024-12-31 | 2024-12-31 | 2025-01-09 |  | 2025-01-16 | 2025-01-28 | 2025-02-26 | 2025-02-11 | 2025-03-26 | 62 | 76
2024-12-27 | 2025-01-22 | 2025-01-29 | 2025-02-04 | 2025-01-29 | 2025-01-29 | 2025-02-06 |  | 2025-02-13 | 2025-02-25 | 2025-03-26 | 2025-03-11 | 2025-04-23 | 60 | 74
2025-01-28 | 2025-02-20 | 2025-02-27 | 2025-03-05 | 2025-02-27 | 2025-02-27 | 2025-03-07 |  | 2025-03-14 | 2025-03-25 | 2025-04-23 | 2025-04-08 | 2025-05-28 | 56 | 70
2025-03-05 | 2025-03-27 | 2025-04-03 | 2025-04-09 | 2025-04-03 | 2025-04-03 | 2025-04-11 |  | 2025-04-18 | 2025-04-22 | 2025-05-28 | 2025-05-13 | 2025-06-25 | 48 | 69
2025-04-01 | 2025-04-23 | 2025-04-30 | 2025-05-06 | 2025-04-30 | 2025-04-30 | 2025-05-08 |  | 2025-05-15 | 2025-05-27 | 2025-06-25 | 2025-06-10 | 2025-07-23 | 56 | 70
2025-04-25 | 2025-05-19 | 2025-05-27 | 2025-06-02 | 2025-05-27 | 2025-05-27 | 2025-06-04 |  | 2025-06-11 | 2025-06-24 | 2025-07-23 | 2025-07-08 | 2025-08-27 | 60 | 74
2025-06-02 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-02 | 2025-07-02 | 2025-07-11 |  | 2025-07-18 | 2025-07-22 | 2025-08-27 | 2025-08-12 | 2025-09-24 | 50 | 71
2025-06-30 | 2025-07-23 | 2025-07-30 | 2025-08-05 | 2025-07-30 | 2025-07-30 | 2025-08-07 |  | 2025-08-14 | 2025-08-26 | 2025-09-24 | 2025-09-09 | 2025-10-22 | 57 | 71
2025-08-04 | 2025-08-26 | 2025-09-03 | 2025-09-09 | 2025-09-03 | 2025-09-03 | 2025-09-11 |  | 2025-09-18 | 2025-09-23 | 2025-10-22 | 2025-10-14 | 2025-11-19 | 50 | 71
2025-08-28 | 2025-09-22 | 2025-09-29 | 2025-10-03 | 2025-09-29 | 2025-09-29 | 2025-10-07 |  | 2025-10-15 | 2025-10-28 | 2025-11-19 | 2025-11-10 | 2025-12-17 | 61 | 74
2025-09-24 | 2025-10-17 | 2025-10-24 | 2025-10-30 | 2025-10-24 | 2025-10-24 | 2025-11-03 |  | 2025-11-12 | 2025-11-18 | 2025-12-17 | 2025-12-09 | 2026-01-28 | 55 | 76
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2026
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2025-10-28 | 2025-11-21 | 2025-12-02 | 2025-12-08 | 2025-12-02 | 2025-12-02 | 2025-12-10 |  | 2025-12-17 | 2025-12-16 | 2026-01-28 | 2026-01-13 | 2026-02-25 | 49 | 77
2025-11-26 | 2025-12-22 | 2025-12-30 | 2026-01-06 | 2025-12-30 | 2025-12-30 | 2026-01-08 |  | 2026-01-15 | 2026-01-27 | 2026-02-25 | 2026-02-10 | 2026-03-25 | 62 | 76
2025-12-26 | 2026-01-21 | 2026-01-28 | 2026-02-03 | 2026-01-28 | 2026-01-28 | 2026-02-05 |  | 2026-02-12 | 2026-02-24 | 2026-03-25 | 2026-03-10 | 2026-04-22 | 60 | 74
2026-02-03 | 2026-02-26 | 2026-03-05 | 2026-03-11 | 2026-03-05 | 2026-03-05 | 2026-03-13 |  | 2026-03-20 | 2026-03-24 | 2026-04-22 | 2026-04-14 | 2026-05-27 | 49 | 70
2026-03-04 | 2026-03-26 | 2026-04-02 | 2026-04-08 | 2026-04-02 | 2026-04-02 | 2026-04-10 |  | 2026-04-17 | 2026-04-28 | 2026-05-27 | 2026-05-12 | 2026-06-24 | 55 | 69
2026-03-31 | 2026-04-22 | 2026-04-29 | 2026-05-05 | 2026-04-29 | 2026-04-29 | 2026-05-07 |  | 2026-05-14 | 2026-05-26 | 2026-06-24 | 2026-06-09 | 2026-07-22 | 56 | 70
2026-05-01 | 2026-05-26 | 2026-06-02 | 2026-06-08 | 2026-06-02 | 2026-06-02 | 2026-06-10 |  | 2026-06-17 | 2026-06-23 | 2026-07-22 | 2026-07-14 | 2026-08-26 | 53 | 74
2026-06-01 | 2026-06-24 | 2026-07-01 | 2026-07-08 | 2026-07-01 | 2026-07-01 | 2026-07-10 |  | 2026-07-17 | 2026-07-28 | 2026-08-26 | 2026-08-11 | 2026-09-23 | 57 | 71
2026-06-29 | 2026-07-22 | 2026-07-29 | 2026-08-04 | 2026-07-29 | 2026-07-29 | 2026-08-06 |  | 2026-08-13 | 2026-08-25 | 2026-09-23 | 2026-09-08 | 2026-10-28 | 57 | 71
2026-08-03 | 2026-08-25 | 2026-09-01 | 2026-09-08 | 2026-09-01 | 2026-09-01 | 2026-09-10 |  | 2026-09-17 | 2026-09-22 | 2026-10-28 | 2026-10-13 | 2026-11-18 | 50 | 71
2026-08-28 | 2026-09-22 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-09-29 | 2026-10-07 |  | 2026-10-15 | 2026-10-27 | 2026-11-18 | 2026-11-10 | 2026-12-16 | 60 | 74
2026-09-23 | 2026-10-16 | 2026-10-23 | 2026-10-29 | 2026-10-23 | 2026-10-23 | 2026-11-02 |  | 2026-11-10 | 2026-11-24 | 2026-12-16 | 2026-12-08 | 2027-01-27 | 62 | 76
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2027
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2026-10-27 | 2026-11-20 | 2026-12-01 | 2026-12-07 | 2026-12-01 | 2026-12-01 | 2026-12-09 |  | 2026-12-16 | 2026-12-22 | 2027-01-27 | 2027-01-12 | 2027-02-24 | 56 | 77
2026-11-25 | 2026-12-21 | 2026-12-29 | 2027-01-05 | 2026-12-29 | 2026-12-29 | 2027-01-07 |  | 2027-01-14 | 2027-01-26 | 2027-02-24 | 2027-02-09 | 2027-03-24 | 62 | 76
2026-12-24 | 2027-01-20 | 2027-01-27 | 2027-02-02 | 2027-01-27 | 2027-01-27 | 2027-02-04 |  | 2027-02-11 | 2027-02-23 | 2027-03-24 | 2027-03-09 | 2027-04-28 | 61 | 75
2027-02-02 | 2027-02-25 | 2027-03-04 | 2027-03-10 | 2027-03-04 | 2027-03-04 | 2027-03-12 |  | 2027-03-19 | 2027-03-23 | 2027-04-28 | 2027-04-13 | 2027-05-26 | 49 | 70
2027-03-03 | 2027-03-25 | 2027-04-01 | 2027-04-07 | 2027-04-01 | 2027-04-01 | 2027-04-09 |  | 2027-04-16 | 2027-04-27 | 2027-05-26 | 2027-05-11 | 2027-06-23 | 55 | 69
2027-03-30 | 2027-04-21 | 2027-04-28 | 2027-05-04 | 2027-04-28 | 2027-04-28 | 2027-05-06 |  | 2027-05-13 | 2027-05-25 | 2027-06-23 | 2027-06-08 | 2027-07-28 | 56 | 70
2027-05-03 | 2027-05-25 | 2027-06-02 | 2027-06-08 | 2027-06-02 | 2027-06-02 | 2027-06-10 |  | 2027-06-17 | 2027-06-22 | 2027-07-28 | 2027-07-13 | 2027-08-25 | 50 | 71
2027-06-01 | 2027-06-23 | 2027-06-30 | 2027-07-07 | 2027-06-30 | 2027-06-30 | 2027-07-09 |  | 2027-07-16 | 2027-07-27 | 2027-08-25 | 2027-08-10 | 2027-09-22 | 56 | 70
2027-07-06 | 2027-07-28 | 2027-08-04 | 2027-08-10 | 2027-08-04 | 2027-08-04 | 2027-08-12 |  | 2027-08-19 | 2027-08-24 | 2027-09-22 | 2027-09-14 | 2027-10-27 | 49 | 70
2027-08-02 | 2027-08-24 | 2027-08-31 | 2027-09-07 | 2027-08-31 | 2027-08-31 | 2027-09-09 |  | 2027-09-16 | 2027-09-28 | 2027-10-27 | 2027-10-12 | 2027-11-17 | 57 | 71
2027-08-27 | 2027-09-21 | 2027-09-28 | 2027-10-04 | 2027-09-28 | 2027-09-28 | 2027-10-06 |  | 2027-10-14 | 2027-10-26 | 2027-11-17 | 2027-11-09 | 2027-12-15 | 60 | 74
2027-09-29 | 2027-10-22 | 2027-10-29 | 2027-11-05 | 2027-10-29 | 2027-10-29 | 2027-11-09 |  | 2027-11-17 | 2027-11-23 | 2027-12-15 | 2027-12-14 | 2028-01-26 | 55 | 76
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2028
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2027-10-27 | 2027-11-22 | 2027-12-01 | 2027-12-07 | 2027-12-01 | 2027-12-01 | 2027-12-09 |  | 2027-12-16 | 2027-12-15 | 2028-01-26 | 2028-01-11 | 2028-02-23 | 49 | 76
2027-11-29 | 2027-12-21 | 2027-12-29 | 2028-01-04 | 2027-12-29 | 2027-12-29 | 2028-01-06 |  | 2028-01-13 | 2028-01-25 | 2028-02-23 | 2028-02-08 | 2028-03-22 | 57 | 71
2028-01-03 | 2028-01-26 | 2028-02-02 | 2028-02-08 | 2028-02-02 | 2028-02-02 | 2028-02-10 |  | 2028-02-17 | 2028-02-22 | 2028-03-22 | 2028-03-14 | 2028-04-26 | 50 | 71
2028-02-01 | 2028-02-24 | 2028-03-02 | 2028-03-08 | 2028-03-02 | 2028-03-02 | 2028-03-10 |  | 2028-03-17 | 2028-03-28 | 2028-04-26 | 2028-04-11 | 2028-05-24 | 56 | 70
2028-03-01 | 2028-03-23 | 2028-03-30 | 2028-04-05 | 2028-03-30 | 2028-03-30 | 2028-04-07 |  | 2028-04-14 | 2028-04-25 | 2028-05-24 | 2028-05-09 | 2028-06-28 | 55 | 69
2028-04-04 | 2028-04-26 | 2028-05-03 | 2028-05-09 | 2028-05-03 | 2028-05-03 | 2028-05-11 |  | 2028-05-18 | 2028-05-23 | 2028-06-28 | 2028-06-13 | 2028-07-26 | 49 | 70
2028-04-28 | 2028-05-22 | 2028-05-30 | 2028-06-05 | 2028-05-30 | 2028-05-30 | 2028-06-07 |  | 2028-06-14 | 2028-06-27 | 2028-07-26 | 2028-07-11 | 2028-08-23 | 60 | 74
2028-05-26 | 2028-06-21 | 2028-06-28 | 2028-07-05 | 2028-06-28 | 2028-06-28 | 2028-07-07 |  | 2028-07-14 | 2028-07-25 | 2028-08-23 | 2028-08-08 | 2028-09-27 | 60 | 74
2028-07-03 | 2028-07-26 | 2028-08-02 | 2028-08-08 | 2028-08-02 | 2028-08-02 | 2028-08-10 |  | 2028-08-17 | 2028-08-22 | 2028-09-27 | 2028-09-12 | 2028-10-25 | 50 | 71
2028-07-31 | 2028-08-22 | 2028-08-29 | 2028-09-05 | 2028-08-29 | 2028-08-29 | 2028-09-07 |  | 2028-09-14 | 2028-09-26 | 2028-10-25 | 2028-10-10 | 2028-11-15 | 57 | 71
2028-08-31 | 2028-09-25 | 2028-10-02 | 2028-10-06 | 2028-10-02 | 2028-10-02 | 2028-10-11 |  | 2028-10-18 | 2028-10-24 | 2028-11-15 | 2028-11-14 | 2028-12-20 | 54 | 75
2028-09-27 | 2028-10-20 | 2028-10-27 | 2028-11-02 | 2028-10-27 | 2028-10-27 | 2028-11-06 |  | 2028-11-15 | 2028-11-28 | 2028-12-20 | 2028-12-12 | 2029-01-24 | 62 | 76
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2029
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2028-10-24 | 2028-11-17 | 2028-11-28 | 2028-12-04 | 2028-11-28 | 2028-11-28 | 2028-12-06 |  | 2028-12-13 | 2028-12-19 | 2028-01-26 | 2029-01-09 | 2029-02-28 | 56 | 77
2028-12-05 | 2028-12-28 | 2029-01-04 | 2029-01-10 | 2029-01-04 | 2029-01-04 | 2029-01-12 |  | 2029-01-19 | 2029-01-25 | 2029-02-28 | 2029-02-13 | 2029-03-28 | 51 | 70
2029-01-02 | 2029-01-24 | 2029-01-31 | 2029-02-06 | 2029-01-31 | 2029-01-31 | 2029-02-08 |  | 2029-02-15 | 2029-02-27 | 2029-03-28 | 2029-03-13 | 2029-04-25 | 56 | 70
2029-01-31 | 2029-02-22 | 2029-03-01 | 2029-03-07 | 2029-03-01 | 2029-03-01 | 2029-03-09 |  | 2029-03-16 | 2029-03-27 | 2029-04-25 | 2029-04-10 | 2029-05-23 | 55 | 69
2029-02-28 | 2029-03-22 | 2029-03-29 | 2029-04-04 | 2029-03-29 | 2029-03-29 | 2029-04-06 |  | 2029-04-13 | 2029-04-24 | 2029-05-23 | 2029-05-08 | 2029-06-27 | 55 | 69
2029-04-03 | 2029-04-25 | 2029-05-02 | 2029-05-08 | 2029-05-02 | 2029-05-02 | 2029-05-10 |  | 2029-05-17 | 2029-05-22 | 2029-06-27 | 2029-06-12 | 2029-07-25 | 49 | 70
2029-04-30 | 2029-05-22 | 2029-05-29 | 2029-06-04 | 2029-05-29 | 2029-05-29 | 2029-06-06 |  | 2029-06-13 | 2029-06-26 | 2029-07-25 | 2029-07-10 | 2029-08-22 | 57 | 71
2029-06-06 | 2029-06-28 | 2029-07-05 | 2029-07-11 | 2029-07-05 | 2029-07-05 | 2029-07-13 |  | 2029-07-20 | 2029-07-24 | 2029-08-22 | 2029-08-14 | 2029-09-26 | 48 | 69
2029-07-03 | 2029-07-25 | 2029-08-01 | 2029-08-07 | 2029-08-01 | 2029-08-01 | 2029-08-09 |  | 2029-08-16 | 2029-08-21 | 2029-09-26 | 2029-09-11 | 2029-10-24 | 49 | 70
2029-07-31 | 2029-08-22 | 2029-08-29 | 2029-09-04 | 2029-08-29 | 2029-08-29 | 2029-09-06 |  | 2029-09-13 | 2029-09-25 | 2029-10-24 | 2029-10-09 | 2029-11-21 | 56 | 70
2029-09-03 | 2029-09-25 | 2029-10-02 | 2029-10-08 | 2029-10-02 | 2029-10-02 | 2029-10-10 |  | 2029-10-17 | 2029-10-23 | 2029-11-21 | 2029-11-13 | 2029-12-19 | 50 | 71
2029-10-01 | 2029-10-23 | 2029-10-30 | 2029-11-05 | 2029-10-30 | 2029-10-30 | 2029-11-07 |  | 2029-11-14 | 2029-11-20 | 2029-12-19 | 2029-12-11 | 2030-01-23 | 50 | 71
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2030
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2029-10-23 | 2029-11-16 | 2029-11-27 | 2029-12-03 | 2029-11-27 | 2029-11-27 | 2029-12-05 |  | 2029-12-12 | 2029-12-19 | 2030-01-23 | 2030-01-08 | 2030-02-27 | 57 | 77
2029-11-30 | 2029-12-24 | 2030-01-02 | 2030-01-08 | 2030-01-02 | 2030-01-02 | 2030-01-10 |  | 2030-01-17 | 2030-01-22 | 2030-02-27 | 2030-02-12 | 2030-03-27 | 53 | 74
2029-12-28 | 2030-01-23 | 2030-01-30 | 2030-02-05 | 2030-01-30 | 2030-01-30 | 2030-02-07 |  | 2030-02-14 | 2030-02-26 | 2030-03-27 | 2030-03-12 | 2030-04-24 | 60 | 74
2030-01-29 | 2030-02-21 | 2030-02-28 | 2030-03-06 | 2030-02-28 | 2030-02-28 | 2030-03-08 |  | 2030-03-15 | 2030-03-26 | 2030-04-24 | 2030-04-09 | 2030-05-22 | 56 | 70
2030-03-06 | 2030-03-28 | 2030-04-04 | 2030-04-10 | 2030-04-04 | 2030-04-04 | 2030-04-12 |  | 2030-04-19 | 2030-04-23 | 2030-05-22 | 2030-05-14 | 2030-06-26 | 48 | 69
2030-04-02 | 2030-04-24 | 2030-05-01 | 2030-05-07 | 2030-05-01 | 2030-05-01 | 2030-05-09 |  | 2030-05-16 | 2030-05-28 | 2030-06-26 | 2030-06-11 | 2030-07-24 | 56 | 70
2030-04-26 | 2030-05-20 | 2030-05-28 | 2030-06-03 | 2030-05-28 | 2030-05-28 | 2030-06-05 |  | 2030-06-12 | 2030-06-25 | 2030-07-24 | 2030-07-09 | 2030-08-28 | 60 | 74
2030-06-03 | 2030-06-26 | 2030-07-03 | 2030-07-10 | 2030-07-03 | 2030-07-03 | 2030-07-12 |  | 2030-07-19 | 2030-07-23 | 2030-08-28 | 2030-08-13 | 2030-09-25 | 50 | 71
2030-07-01 | 2030-07-24 | 2030-07-31 | 2030-08-06 | 2030-07-31 | 2030-07-31 | 2030-08-08 |  | 2030-08-15 | 2030-08-27 | 2030-09-25 | 2030-09-10 | 2030-10-23 | 57 | 71
2030-07-30 | 2030-08-21 | 2030-08-28 | 2030-09-04 | 2030-08-28 | 2030-08-28 | 2030-09-06 |  | 2030-09-13 | 2030-09-24 | 2030-10-23 | 2030-10-08 | 2030-11-20 | 56 | 70
2030-08-29 | 2030-09-23 | 2030-09-30 | 2030-10-04 | 2030-09-30 | 2030-09-30 | 2030-10-08 |  | 2030-10-16 | 2030-10-22 | 2030-11-20 | 2030-11-12 | 2030-12-18 | 54 | 75
2030-09-25 | 2030-10-18 | 2030-10-25 | 2030-10-31 | 2030-10-25 | 2030-10-25 | 2030-11-04 |  | 2030-11-13 | 2030-11-19 | 2030-12-18 | 2030-12-10 | 2031-01-22 | 55 | 76
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
VIRGINIA DEPARTMENT OF TRANSPORTATION CONTRACT DOCUMENTS AND PROCESSING CUT-OFF DATES FOR ADVERTISEMENT OF TIER 1 CONSTRUCTION AND MAINTENANCE PROJECTS 2031
IF DISTRICT REQUESTS BID-ABILITY REVIEW |  |  |  | ASSEMBLY (PLANS & CONTRACT DOCUMENTS) SUBMISSION TO SCD FOR SAAP PROJECTS | PLAN SUBMISSION TO SCD FOR PROJECTS WITH "NO" BID-ABILITY REVIEW | ADVERTISEMENT SUBMISSION TO SCD PRINT REPRODUCTION OF PLANS | RIGHT OF WAY CERTIFICATION 69X | Request to FHWA for Authorization to Advertise | "NOT FEDERALLY ELIGIBLE / EXEMPT" |  | "FEDERALLY ELIGIBLE" |  | Rev 9/1/20
PLAN SUBMISSION TO SCD AND CONTRACT DEVELOPMENT BEGINS | SCD CONTRACT DEVELOPMENT COMPLETED AND DISTRICT BID-ABILITY REVIEW BEGINS | DISTRICT BID-ABILITY REVIEW ENDS AND DISTRICT COMMENTS SENT TO SCD | REVISIONS TO CONTRACT DOCUMENTS BY SCD PER BID-ABILITY REVIEW ENDS (GO TO COLUMN 7)
[9 empty] | ADVERTISEMENT | BID LETTING | ADVERTISEMENT | BID LETTING | Actual Calendar Days State Funded | Actual Calendar Days Federal Funded
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 (S) | 10 (S) | 9 (F) | 10 (F)
2030-10-29 | 2030-11-22 | 2030-12-03 | 2030-12-09 | 2030-12-03 | 2030-12-03 | 2030-12-11 |  | 2030-12-18 | 2030-12-17 | 2031-01-22 | 2031-01-14 | 2031-02-26 | 49 | 77
2030-12-04 | 2030-12-26 | 2031-01-02 | 2031-01-08 | 2031-01-02 | 2031-01-02 | 2031-01-10 |  | 2031-01-17 | 2031-01-28 | 2031-02-26 | 2031-02-11 | 2031-03-26 | 55 | 69
2031-01-01 | 2031-01-23 | 2031-01-30 | 2031-02-05 | 2031-01-30 | 2031-01-30 | 2031-02-07 |  | 2031-02-14 | 2031-02-25 | 2031-03-26 | 2031-03-11 | 2031-04-23 | 55 | 69
2031-01-29 | 2031-02-20 | 2031-02-27 | 2031-03-05 | 2031-02-27 | 2031-02-27 | 2031-03-07 |  | 2031-03-14 | 2031-03-25 | 2031-04-23 | 2031-04-08 | 2031-05-28 | 55 | 69
2031-03-05 | 2031-03-27 | 2031-04-03 | 2031-04-09 | 2031-04-03 | 2031-04-03 | 2031-04-11 |  | 2031-04-18 | 2031-04-22 | 2031-05-28 | 2031-05-13 | 2031-06-25 | 48 | 69
2031-04-02 | 2031-04-24 | 2031-05-01 | 2031-05-07 | 2031-05-01 | 2031-05-01 | 2031-05-09 |  | 2031-05-16 | 2031-05-27 | 2031-06-25 | 2031-06-10 | 2031-07-23 | 55 | 69
2031-04-30 | 2031-05-22 | 2031-05-29 | 2031-06-04 | 2031-05-29 | 2031-05-29 | 2031-06-06 |  | 2031-06-13 | 2031-06-24 | 2031-07-23 | 2031-07-08 | 2031-08-27 | 55 | 69
2031-06-04 | 2031-06-26 | 2031-07-03 | 2031-07-09 | 2031-07-03 | 2031-07-03 | 2031-07-11 |  | 2031-07-18 | 2031-07-22 | 2031-08-27 | 2031-08-12 | 2031-09-24 | 48 | 69
2031-07-02 | 2031-07-24 | 2031-07-31 | 2031-08-06 | 2031-07-31 | 2031-07-31 | 2031-08-08 |  | 2031-08-15 | 2031-08-28 | 2031-09-24 | 2031-09-09 | 2031-10-22 | 57 | 69
2031-08-06 | 2031-08-28 | 2031-09-04 | 2031-09-10 | 2031-09-04 | 2031-09-04 | 2031-09-12 |  | 2031-09-19 | 2031-09-23 | 2031-10-22 | 2031-10-14 | 2031-11-19 | 48 | 69
2031-09-02 | 2031-09-24 | 2031-10-01 | 2031-10-07 | 2031-10-01 | 2031-10-01 | 2031-10-09 |  | 2031-10-16 | 2031-10-28 | 2031-11-19 | 2031-11-10 | 2031-12-17 | 56 | 69
2031-10-01 | 2031-10-23 | 2031-10-30 | 2031-11-05 | 2031-10-30 | 2031-10-30 | 2031-11-07 |  | 2031-11-14 | 2031-11-19 | 2031-12-17 | 2031-12-09 | 2031-01-22 | 49 | 69
71 BEG | 72 BEG | 72B BEG | 72B END |  | 71 BEG |  |  | 80 BEG | 80 END |  | 80 END
|  | 79 BEG | 63 END |  |  | 21A,B,H, S END |  | 72 END
|  | *67C,D,U END |  | *67C,D,U END | *67C,D,U END
|  | 69, 69R END |  | 69, 69R END | 69, 69R END
|  | 63 END |  | 63 END | 63 END
|  | 71 END |  | 71 END | 71 END
Note on A3: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A26: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A49: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A72: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A95: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A118: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A141: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A164: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A187: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A210: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A233: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A256: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A279: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on A302: ie.lewis: Column 1: Plan Submission to SCD and Contract Development Begins By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 1 to 2 Duration: 16 Working Days
Note on B3: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B26: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B49: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B72: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B95: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B118: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B141: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B164: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B187: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B210: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B233: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B256: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B279: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on B302: ie.lewis: Column 2: SCD Contract Development Completed and District Bid-Ability Review Begins By this date, contract documents (electronic proposal) are completed for the Bidability Review and are available electronically at \0501coitd\const\public\proposals. The Scheduling and Contract Division formally notifies the Project Manager, the Responsible Charge Engineer and the District Construction (Maintenance) Engineer that the completed bid proposal has been posted to the server. The Project Manager ensures that the Bidability team has all information needed for their review. On this date, the Schedule and Contract Division will establish a project file to contain permits and project specific special provisions. Scheduling nd Contract Division begins building the control estimate and proposal. Activity 72, Prepare Proposal, begins on this date. Also by this date, the Environmental Quality Division will submit the Environmental Certification Checklist and Environmental Verification at PS&E Stage forms to the Scheduling and Contract Division. • Column 2 to 3 Duration: 5 Working Days
Note on C3: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C26: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C49: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C72: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C95: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C118: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C141: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C164: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C187: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C210: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C233: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C256: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C279: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on C302: ie.lewis: Column 3: District Bid-Ability Ends and District Comments sent to SCD By this date, the Project Manager posts the findings of the Bidability team to IPM and notifies Scheduling and Contract Division that the report has been posted. This review shall consist of a check to ensure that contract documents agree with the plans, specifications and special provisions. No new requests will be allowed. Programming Division provides verification to Project Manager and Schedule and Contract Division that Control Estimate does not trigger STIP or funding issues. Programming issues Funding Approval for Construction, Form PD-4. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. Scheduling and Cotracts Division completes a Control Estimate and notifies the PM and the funding Division if there is significant variance from the initial engineeers estimate. Activity 72B, Bidability Review, and Activity 79, Approve Construction Funds, begin on this date. • Column 3 to 4 Duration: 4 Working Days
Note on D3: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D26: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D49: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D72: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D95: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D118: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D141: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D164: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D187: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D210: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D233: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D256: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D279: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on D302: ie.lewis: Column 4: Revisions to Contract Documents by SCD per Bidability Review Ends By this Date, any necessary revisions to the contract documents, as the result of the Bidability review, are completed by Scheduling and Contract Division. Activity 63 and 72B, Bidability Review, end on this date. • Column 4 to 5 Duration: 2 Working Days
Note on E2: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E25: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E48: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E71: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E94: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E117: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E140: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E163: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E186: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E209: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E232: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E255: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E278: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on E301: ie.lewis: Column 5: Assembly (Plans & Contract Documents) Submission to SCD for SAAP Projects By this date, SAAP Projects are completed and submitted to Scheduling and Contract Division. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. • Column 5 to 7 Duration: 6 Working Days
Note on F2: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F25: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F48: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F71: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F94: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F117: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F140: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F163: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F186: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F209: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F232: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F255: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F278: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on F301: ie.lewis: Column 6: Plan Submission to SCD For Projects With "No" Bid-Ability Review By this date, all revisions to the project plan assembly must be completed. All revisions resulting from the QC and Constructability Reviews and the Pre Advertisement Conference must be completed. The final cost estimate must be updated in TRANSPORT, with bid-based items regenerated. The final CEI (Construction Engineering and Inspection) budget must be transmitted to the Project Manager. Any special contract language and all specifications, special provisions and copied notes and the proposed CPM (Critical Path Management) schedule must be transmitted by the Project Manager. By this date, the Project Manager must notify the SCD of the electronic availability of, the complete plan assembly, any required forms, any special contract language, specifications, project specific special provisions or copied notes, the CEI Budget and the TRANSPORT engineer’s estimate. Also by this date the following disciplines must provide the following information: The Project Manager should have requested the Environmental Division to transmit the NEPA environmental documents to the Scheduling and Contract Division (PM-130). The Rail and Public Transportation section must have all necessary railroad agreements. Disposition of comments received (acceptance, rejection or modification) should be made in writing to each discipline involved in the Quality Control Review, Constructability Review and Pre-Advertisement Conference by the Project Manager prior to this date. PM Certification is complete at this point. Activity 71, Approved Construction Plans, Begins. By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Divison. Activities 67C,67D, 67U, 69 and 69R must be completed by this date. Activities 63, 71 end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 6 to 7 Duration: 6 Working Days
Note on G2: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G25: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G48: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G71: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G94: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G117: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G140: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G163: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G186: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G209: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G232: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G255: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G278: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on G301: ie.lewis: Column 7: Advertisement Submission to SCD Print Reproduction of Plans Right of Way Certification By this date, the Right-of-Way and Utility Division will submit the right-of-way releases to the Scheduling and Contract Division. Activities 21A, 21B, 21H, and 21S end on this date. For Sealing and Signing requirements, see Construction Division CD-2009-03, which can be accessed at http://www.virginiadot.org/business/resources/const/cdmemo-0903.pdf. • Column 7 to 8 Duration: 5 Working Days
Note on I2: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I25: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I48: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I71: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I94: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I117: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I140: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I163: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I186: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I209: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I232: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I255: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I278: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on I301: ie.lewis: Column 8: Request to FHWA for Authorization to Advertise By this date, the complete PS&E assembly will be submitted by the Scheduling and Contract Division the Federal Coordinator in Programming. Activities 72 end and Activity 80, Advertise Project, begins. • Column 8 to 9(F) Duration: 17 Working Days
Note on J4: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J27: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J50: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J73: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J96: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J119: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J142: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J165: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J188: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J211: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J234: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J257: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J280: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on J303: ie.lewis: Column 9(S): Advertisement On this date, for state funded projects only, the project is advertised. It is the first available SAAP advertisement date. Activity 80 ends.
Note on K4: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K27: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K50: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K73: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K96: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K119: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K142: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K165: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K188: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K211: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K234: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K257: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K280: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on K303: ie.lewis: Column 10 (S) Bid Letting On this date the bids on state funded NP will be received from contractors.
Note on L4: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L27: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L50: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L73: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L96: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L142: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L165: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L188: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L211: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L234: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L257: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on L280: ie.lewis: Column 9 (F): Advertisement On this date, Federally Funded Projects are advertised. Activity 80 ends.
Note on M4: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M27: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M50: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M73: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M96: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M142: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M165: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M188: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M211: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M234: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M257: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.
Note on M280: ie.lewis: Column 10 (F): Bid Letting On this date, federally funded NP will be received from contractors.

## Holidays
New Years Day | 2018-01-01 | 2018
Lee-Jackson Day | 2018-01-12
Martin Luther King, Jr. Day | 2018-01-15
Presidents Day | 2018-02-19
Memorial Day | 2018-05-28
Independence Day | 2018-07-04
Labor Day | 2018-09-03
Columbus Day | 2018-10-08
Veterans Day | 2018-11-12
Thanksgiving Day | 2018-11-22
Day After Thanksgiving | 2018-11-23
Christmas Day | 2018-12-25
New Years Day | 2019-01-01 | 2019
Lee-Jackson Day | 2019-01-18
Martin Luther King, Jr. Day | 2019-01-21
Presidents Day | 2019-02-16
Memorial Day | 2019-05-27
Independence Day | 2019-07-04
Labor Day | 2019-09-02
Columbus Day | 2019-10-14
Veterans Day | 2019-11-11
Thanksgiving Day | 2019-11-28
Day After Thanksgiving | 2019-11-29
Christmas Day | 2019-12-25
New Years Day | 2020-01-01 | 2020
Lee-Jackson Day | 2020-01-17
Martin Luther King, Jr. Day | 2020-01-20
Presidents Day | 2020-02-17
Memorial Day | 2020-05-25
Independence Day | 2020-07-04
Labor Day | 2020-09-07
Columbus Day | 2020-10-12
Veterans Day | 2020-11-11
Thanksgiving Day | 2020-11-26
Day After Thanksgiving | 2020-11-27
Christmas Day | 2020-12-25
New Years Day | 2021-01-01 | 2021
Lee-Jackson Day | 2021-01-15
Martin Luther King, Jr. Day | 2021-01-18
Presidents Day | 2021-02-15
Memorial Day | 2021-05-31
Independence Day | 2021-07-05
Labor Day | 2021-09-06
Columbus Day | 2021-10-11
Veterans Day | 2021-11-11
Thanksgiving Day | 2021-11-25
Day After Thanksgiving | 2021-11-26
Christmas Day | 2021-12-25
New Years Day | 2022-01-01 | 2022
Lee-Jackson Day | 2022-01-14
Martin Luther King, Jr. Day | 2022-01-17
Presidents Day | 2022-02-21
Memorial Day | 2022-05-30
Independence Day | 2022-07-04
Labor Day | 2022-09-05
Columbus Day | 2022-10-10
Veterans Day | 2022-11-11
Thanksgiving Day | 2022-11-24
Day After Thanksgiving | 2022-11-25
Christmas Day | 2022-12-26
New Years Day | 2023-01-02 | 2023
Lee-Jackson Day | 2023-01-13
Martin Luther King, Jr. Day | 2023-01-16
Presidents Day | 2023-02-20
Memorial Day | 2023-05-29
Independence Day | 2023-07-04
Labor Day | 2023-09-04
Columbus Day | 2023-10-09
Veterans Day | 2023-11-10
Thanksgiving Day | 2023-11-23
Day After Thanksgiving | 2023-11-24
Christmas Day | 2023-12-25
New Years Day | 2024-01-01 | 2024
Martin Luther King, Jr. Day | 2024-01-15
Presidents Day | 2024-02-19
Memorial Day | 2024-05-27
Juneteenth | 2024-06-19
Independence Day | 2024-07-04
Labor Day | 2024-09-02
Columbus Day | 2024-10-14
Voting Day | 2024-11-05
Veterans Day | 2024-11-11
Thanksgiving Day | 2024-11-28
Day After Thanksgiving | 2024-11-29
Christmas Day | 2024-12-25
New Years Day | 2025-01-01 | 2025
Martin Luther King, Jr. Day | 2025-01-20
Presidents Day | 2025-02-17
Memorial Day | 2025-05-26
Juneteenth | 2025-06-19
Independence Day | 2025-07-04
Labor Day | 2025-09-01
Columbus Day | 2025-10-13
Voting Day | 2025-11-04
Veterans Day | 2025-11-11
Thanksgiving Day | 2025-11-27
Day After Thanksgiving | 2025-11-28
Christmas Day | 2025-12-25
New Years Day | 2026-01-01 | 2026
Martin Luther King, Jr. Day | 2026-01-19
Presidents Day | 2026-02-16
Memorial Day | 2026-05-25
Juneteenth | 2026-06-19
Independence Day | 2026-07-03
Labor Day | 2026-09-07
Columbus Day | 2026-10-12
Voting Day | 2026-11-03
Veterans Day | 2026-11-11
Thanksgiving Day | 2026-11-26
Day After Thanksgiving | 2026-11-27
Christmas Day | 2026-12-25
New Years Day | 2027-01-01 | 2027
Martin Luther King, Jr. Day | 2027-01-18
Presidents Day | 2027-02-15
Memorial Day | 2027-05-31
Juneteenth | 2027-06-19
Independence Day | 2027-07-05
Labor Day | 2027-09-06
Columbus Day | 2027-10-11
Voting Day | 2027-11-02
Veterans Day | 2027-11-11
Thanksgiving Day | 2027-11-25
Day After Thanksgiving | 2027-11-26
Christmas Day | 2027-12-24
New Years Day | 2028-01-01 | 2028
Martin Luther King, Jr. Day | 2028-01-17
Presidents Day | 2028-02-21
Memorial Day | 2028-05-29
Juneteenth | 2028-06-19 |  | Saturday; May change based on State Holiday
Independence Day | 2028-07-04
Labor Day | 2028-09-04
Columbus Day | 2028-10-09
Voting Day | 2028-11-07
Veterans Day | 2028-11-10
Thanksgiving Day | 2028-11-23
Day After Thanksgiving | 2028-11-24
Christmas Day | 2028-12-25
New Years Day | 2029-01-01 | 2029
Martin Luther King, Jr. Day | 2029-01-15
Presidents Day | 2029-02-19
Memorial Day | 2029-05-28
Juneteenth | 2029-06-19
Independence Day | 2029-07-04
Labor Day | 2029-09-03
Columbus Day | 2029-10-08
Voting Day | 2029-11-06
Veterans Day | 2029-11-12
Thanksgiving Day | 2029-11-22
Day After Thanksgiving | 2029-11-23
Christmas Day | 2029-12-25
New Years Day | 2030-01-01 | 2030
Martin Luther King, Jr. Day | 2030-01-21
Presidents Day | 2030-02-18
Memorial Day | 2030-05-27
Juneteenth | 2030-06-19
Independence Day | 2030-07-04
Labor Day | 2030-09-02
Columbus Day | 2030-10-14
Voting Day | 2030-11-05
Veterans Day | 2030-11-11
Thanksgiving Day | 2030-11-28
Day After Thanksgiving | 2030-11-29
Christmas Day | 2030-12-25
New Years Day | 2031-01-01 | 2031
Martin Luther King, Jr. Day | 2031-01-20
Presidents Day | 2031-02-17
Memorial Day | 2031-05-26
Juneteenth | 2031-06-19
Independence Day | 2031-07-04
Labor Day | 2031-09-01
Columbus Day | 2031-10-13
Voting Day | 1931-11-04
Veterans Day | 2031-11-11
Thanksgiving Day | 2031-11-27
Day After Thanksgiving | 2031-11-28
Christmas Day | 2031-12-25